## Product Backlog
Story ID | Story Name | User Role | Description (User Story) | Acceptance Criteria | Priority | Sprint | Estimation (Story Points) | Assignee | Date Started (Planned) | Date Finished (Planned) | Status | Notes
1 | User Login & Role-Based Access | All Users | As a user (TA/MO/Admin), I want to log in with my credentials and be directed to my role-specific dashboard, So that I can access features relevant to my role. | 1. Login form with username and password fields. 2. Invalid credentials show clear error message. 3. Successful login redirects to role-specific dashboard (TA/MO/Admin). 4. Session maintained until logout. | Must Have | Sprint 1 | 3 | Yi Qi | 2026-03-08 | 2026-03-14 | Planned | Servlet + Session. Users stored in users.json.
2 | TA Profile Creation & Editing | TA | As a TA applicant, I want to create and edit my profile (name, student ID, email, programme, skills, availability), So that my information is ready for job applications. | 1. TA fills required fields: name, student ID, email, programme, skills, availability. 2. System validates required fields; shows errors for empty ones. 3. Profile stored in data/ta_profiles.json. 4. Profile can be viewed and edited later. | Must Have | Sprint 1 | 3 | Tianyu Zhao | 2026-03-08 | 2026-03-14 | Planned | Store in data/ta_profiles.json. JSP form.
3 | MO Post TA Position | MO | As a Module Organiser, I want to post a TA position with module code, required skills, hours, and deadline, So that qualified students can find and apply. | 1. MO enters: module code, name, TA count, required skills, weekly hours, deadline, description. 2. Prevents submission if required fields empty. 3. Position appears in public job list after saving. 4. Stored in data/jobs.json with status "Open". | Must Have | Sprint 1 | 3 | Jie Ren | 2026-03-08 | 2026-03-14 | Planned | Store in data/jobs.json.
4 | Browse Available TA Positions | TA | As a TA applicant, I want to browse all open TA positions with module name, skills, hours, and deadline, So that I can find suitable positions. | 1. List all jobs with status "Open". 2. Shows: module code, name, required skills, hours/week, deadline, positions count. 3. Past-deadline jobs marked "Closed" and greyed out. 4. Sortable by deadline or module name. | Must Have | Sprint 1 | 2 | Haopeng Jin | 2026-03-08 | 2026-03-14 | Planned | Read from data/jobs.json. JSP list view.
5 | TA Apply for Position | TA | As a TA applicant, I want to apply for a specific TA position, So that the Module Organiser can consider me. | 1. TA clicks "Apply" on an open listing. 2. System checks TA has completed profile. 3. Application recorded in data/applications.json with status "Pending". 4. Confirmation message shown. 5. Cannot apply twice for same position. | Must Have | Sprint 1 | 3 | Zhuang Hou | 2026-03-08 | 2026-03-14 | Planned | Store in data/applications.json.
6 | TA Upload CV | TA | As a TA applicant, I want to upload my CV file, So that Module Organisers can review my qualifications. | 1. Upload file (PDF/DOC, max 5MB) from profile page. 2. System validates file type and size. 3. Saved to data/cv/ as studentID_cv.pdf. 4. Success/failure message shown. 5. Can replace previously uploaded CV. | Must Have | Sprint 1 | 3 | Zexuan Dong | 2026-03-08 | 2026-03-14 | Planned | File upload servlet. Store in data/cv/.
7 | MO View Applicant List & CV | MO | As a Module Organiser, I want to view all applicants for my position and read their CVs, So that I can evaluate each candidate. | 1. List all applicants for each posted job. 2. Shows: name, skills, availability, application date. 3. MO can view/download applicant CV. 4. Shows total applicant count per position. | Must Have | Sprint 2 | 3 | Yi Qi | 2026-03-15 | 2026-03-22 | Planned | Join applications.json + ta_profiles.json.
8 | MO Accept / Reject Application | MO | As a Module Organiser, I want to accept or reject each application, So that I can select the best candidates. | 1. Change status to "Accepted" or "Rejected" per applicant. 2. Confirmation dialog before status change. 3. Updated in data/applications.json. 4. Accepted count cannot exceed posted positions. | Must Have | Sprint 2 | 3 | Tianyu Zhao | 2026-03-15 | 2026-03-22 | Planned | Status update in applications.json.
9 | TA Check Application Status | TA | As a TA applicant, I want to check the status of all my applications, So that I know which are accepted, rejected, or pending. | 1. TA dashboard lists all submitted applications. 2. Shows: module name, date, status (Pending/Accepted/Rejected). 3. Status reflects MO decisions in real-time. 4. History of all past applications visible. | Must Have | Sprint 2 | 2 | Jie Ren | 2026-03-15 | 2026-03-22 | Planned | Filter applications.json by TA student ID.
10 | Admin Recruitment Overview Dashboard | Admin | As an Administrator, I want to see an overview of all open positions and application counts, So that I can monitor overall recruitment progress. | 1. Table of all positions with: module, MO, positions, applicants, status. 2. Filter by status (Open/Closed) or module. 3. Summary: total open positions, total applicants. 4. Dashboard loads within 2 seconds. | Must Have | Sprint 2 | 3 | Haopeng Jin | 2026-03-15 | 2026-03-22 | Planned | Aggregate jobs.json + applications.json.
11 | JSON Data Persistence Layer | All Users | As a system user, I want all data reliably stored in JSON files, So that information persists between sessions. | 1. Profiles in data/ta_profiles.json. 2. Jobs in data/jobs.json. 3. Applications in data/applications.json. 4. Thread-safe read/write with file locking. 5. Consistent schema documented. | Must Have | Sprint 2 | 2 | Zhuang Hou | 2026-03-15 | 2026-03-22 | Planned | Utility class: JsonFileManager.java.
12 | User Registration & Password Hashing | All Users | As a new user, I want to register an account with secure password, So that my account is protected. | 1. Registration: username, password, confirm password, role. 2. Password >= 8 characters. 3. Passwords hashed (SHA-256) before storage. 4. Duplicate usernames rejected. 5. Stored in data/users.json. | Must Have | Sprint 2 | 3 | Zexuan Dong | 2026-03-15 | 2026-03-22 | Planned | Password hashing. data/users.json.
13 | Responsive & Consistent UI | All Users | As a user, I want a clean, easy-to-navigate interface, So that I can complete tasks efficiently. | 1. Consistent layout, color scheme, navigation across all pages. 2. Role-specific nav bar items. 3. Clear form labels and inline validation. 4. Pages load within 2 seconds. | Should Have | Sprint 3 | 3 | Yi Qi | 2026-03-29 | 2026-04-12 | Planned | CSS + JSP layout template.
14 | TA Job Search & Filter | TA | As a TA applicant, I want to search/filter jobs by skill, module name, and hours, So that I can quickly find matching positions. | 1. Search bar for keyword search (module/skill). 2. Filters: skills (checkbox), hours (range), deadline. 3. Results update dynamically. 4. "Clear filters" resets to full list. | Should Have | Sprint 3 | 3 | Tianyu Zhao | 2026-03-29 | 2026-04-12 | Planned | Client-side filtering with JavaScript.
15 | Admin Historical Recruitment Records | Admin | As an Administrator, I want to view past recruitment records, So that I can review completed cycles and trends. | 1. View past records by semester. 2. Each shows: module, MO, selected TAs, dates. 3. Searchable by module or semester. 4. Closed positions auto-archived. | Should Have | Sprint 3 | 3 | Jie Ren | 2026-03-29 | 2026-04-12 | Planned | Archive logic in JsonFileManager.
16 | Real-Time Applicant Count | TA | As a TA applicant, I want to see how many people applied for each position, So that I can gauge competition. | 1. Applicant count shown next to each job listing. 2. Count updates after each new application. 3. Count matches actual applications in JSON. 4. High-competition (>10) highlighted. | Should Have | Sprint 3 | 2 | Haopeng Jin | 2026-03-29 | 2026-04-12 | Planned | Count from applications.json per job.
17 | Privacy & Role-Based Access Control | All Users | As a user, I want my private data (CV, contact) visible only to authorized roles, So that my information is protected. | 1. CV visible only to MOs for positions TA applied to. 2. Admin sees statistics only, not individual CVs. 3. TAs cannot view other TAs' data. 4. Session timeout after 30 min. | Should Have | Sprint 3 | 3 | Zhuang Hou | 2026-03-29 | 2026-04-12 | Planned | Servlet filter for access control.
18 | MO Edit / Close Job Posting | MO | As a Module Organiser, I want to edit or close my posted position, So that I can update requirements or stop applications. | 1. MO can edit all fields of own posted position. 2. MO can close position (status → "Closed"). 3. Closing prevents new applications. 4. Existing applications preserved. | Should Have | Sprint 3 | 2 | Zexuan Dong | 2026-03-29 | 2026-04-12 | Planned | Edit form + status toggle.
19 | AI Skill Matching & Ranking | MO | As a Module Organiser, I want the system to rank applicants by skill match score, So that I can quickly identify best candidates. | 1. Compares TA skills with job requirements. 2. Match score (0-100%) displayed. 3. Sortable by match score. 4. Shows matched vs missing skills. 5. Algorithm is explainable. | Could Have | Sprint 4 | 5 | Yi Qi | 2026-04-19 | 2026-05-18 | Done | Done - 6D recommendation score and MO candidate ranking implemented.
20 | AI Missing Skills Identification | TA | As a TA applicant, I want to see what skills I'm missing for a position, So that I can improve my qualifications. | 1. "Check My Fit" button on job detail page. 2. Compares profile skills with job requirements. 3. Matched skills in green, missing in red. 4. Improvement suggestions displayed. | Could Have | Sprint 4 | 3 | Tianyu Zhao | 2026-04-19 | 2026-05-18 | Done | Done - matched and missing skills shown on TA dashboard and job detail.
21 | Admin Workload Monitoring & Alerts | Admin | As an Administrator, I want to monitor TA workloads and see overload alerts, So that no TA is assigned too many modules. | 1. Dashboard shows each TA's total accepted hours/week. 2. Configurable limit (e.g., max 20 hrs/week). 3. Over-limit TAs highlighted in red. 4. Workload summary report exportable. | Could Have | Sprint 4 | 5 | Jie Ren | 2026-04-19 | 2026-05-18 | Done | Done - Admin workload monitoring and workload CSV export implemented.
22 | Export Recruitment Data as CSV | Admin | As an Administrator, I want to export recruitment data as CSV, So that I can share reports with management. | 1. Export options: positions, applications, workload. 2. Generates downloadable CSV file. 3. CSV includes all relevant columns with headers. 4. Filename includes export date. | Could Have | Sprint 4 | 3 | Haopeng Jin | 2026-04-19 | 2026-05-18 | Done | Done - Admin CSV export endpoint supports jobs, applications, and workload.
23 | In-System Notification for Status Change | TA | As a TA applicant, I want to receive a notification when my application status changes, So that I don't need to check manually. | 1. Notification created when MO accepts/rejects. 2. Dashboard shows unread notification count. 3. Shows: module name, new status, date. 4. Can mark as read. | Could Have | Sprint 4 | 3 | Zhuang Hou | 2026-04-19 | 2026-05-18 | Done | Done - TA notifications created on MO status updates with mark-as-read flow.
24 | Unit & Integration Testing | All Users | As a developer, I want comprehensive test coverage for core features, So that the system is reliable. | 1. JUnit tests for JSON read/write. 2. Tests for login authentication. 3. Tests for application workflow. 4. Integration tests for user flows. 5. Coverage report generated. | Could Have | Sprint 4 | 5 | Zexuan Dong | 2026-04-19 | 2026-05-18 | Done | Done - JUnit tests plus JaCoCo coverage report via mvn verify.

## Sprint Summary
Sprint | Iteration | Date Range | Total Story Points | Stories Count | Focus Area
Sprint 1 | Iteration 1 (前半) | 2026-03-08 → 2026-03-14 | 17 | 6 | Core: Login, TA Profile, MO Post Job, Browse Jobs, Apply, CV Upload
Sprint 2 | Iteration 1 (后半) | 2026-03-15 → 2026-03-22 | 16 | 6 | Review: MO View Applicants, Accept/Reject, Check Status, Admin Overview, JSON Layer, Registration
Sprint 3 | Iteration 2 | 2026-03-29 → 2026-04-12 | 16 | 6 | Polish: UI Design, Search/Filter, History, Applicant Count, Privacy, Edit/Close Job
Sprint 4 | Iteration 3+4 | 2026-04-19 → 2026-05-24 | 24 | 6 | AI+Testing complete: ranking, skill gaps, workload monitoring/export, notifications, tests/coverage
Total |  |  | 73 | 24

## Member Assignment
Member | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Total
Yi Qi | #1 User Login & Role-Based Access | #7 MO View Applicant List & CV | #13 Responsive & Consistent UI | #19 AI Skill Matching & Ranking | 4
Tianyu Zhao | #2 TA Profile Creation & Editing | #8 MO Accept / Reject Application | #14 TA Job Search & Filter | #20 AI Missing Skills Identification | 4
Jie Ren | #3 MO Post TA Position | #9 TA Check Application Status | #15 Admin Historical Recruitment Records | #21 Admin Workload Monitoring & Alerts | 4
Haopeng Jin | #4 Browse Available TA Positions | #10 Admin Recruitment Overview Dashboard | #16 Real-Time Applicant Count | #22 Export Recruitment Data as CSV | 4
Zhuang Hou | #5 TA Apply for Position | #11 JSON Data Persistence Layer | #17 Privacy & Role-Based Access Control | #23 In-System Notification for Status Change | 4
Zexuan Dong | #6 TA Upload CV | #12 User Registration & Password Hashing | #18 MO Edit / Close Job Posting | #24 Unit & Integration Testing | 4