## ProductBacklog
Story ID | Epic | User/Actor | User Story | Acceptance Criteria | Priority | Estimate (SP) | Iteration | Scope | Rationale
PB-01 | Authentication & Roles | All users | As a user, I want to sign in with a role-aware account so that I can access the correct functions. | Given a valid username and password, login succeeds; invalid credentials show a clear error; the user is routed to the correct dashboard based on role. | Must | 5 | Iteration 1 | Core | Required to access every other feature.
PB-02 | Profile Management | TA | As a TA, I want to create and edit my profile so that I can present my background to recruiters. | TA can enter name, student ID, programme, skills, availability, and prior experience; required fields are validated; profile changes are saved to text-based storage. | Must | 5 | Iteration 1 | Core | Directly supports recruitment decisions.
PB-03 | CV Handling | TA | As a TA, I want to paste or upload CV text so that the system can use it for matching and review. | System accepts CV as plain text or .txt content; saved content is linked to the applicant profile; MO can read the stored CV content. | Must | 3 | Iteration 1 | Core | Meets text-file storage restriction.
PB-04 | Job Discovery | TA | As a TA, I want to browse open jobs so that I can decide what to apply for. | TA can see a list of open jobs with title, module, deadline, workload and status; closed jobs are clearly marked or hidden; data loads from text-based storage. | Must | 3 | Iteration 1 | Core | Core customer journey.
PB-05 | Job Search | TA | As a TA, I want to search and filter jobs so that I can quickly find relevant opportunities. | TA can filter by module, skill, date or keyword; filtered results update correctly; reset restores the full list. | Should | 3 | Iteration 2 | Extension | Improves usability and demo quality.
PB-06 | Job Details | TA | As a TA, I want to view detailed job requirements so that I can judge whether I am suitable. | Job detail page shows responsibilities, required skills, preferred skills, schedule, deadline and quota; missing or expired jobs show a clear message. | Must | 2 | Iteration 1 | Core | Needed before application.
PB-07 | Application Submission | TA | As a TA, I want to apply for a job so that I can be considered for the role. | TA can submit one application per job; duplicate submission is blocked; successful submission creates an application record with timestamp and initial status. | Must | 5 | Iteration 2 | Core | Central business flow.
PB-08 | Application Tracking | TA | As a TA, I want to track my application status so that I know whether I am shortlisted, accepted or rejected. | TA dashboard shows every submitted application and current status; status updates become visible after MO action; unknown application IDs are handled safely. | Must | 3 | Iteration 2 | Core | Suggested explicitly in handout.
PB-09 | Application Withdrawal | TA | As a TA, I want to withdraw an application before the deadline so that I can correct mistakes or change my plan. | Withdraw option is available only before the deadline and before final decision; withdrawn status is stored and visible; workload is not counted for withdrawn applications. | Could | 3 | Iteration 3 | Extension | Good usability extension.
PB-10 | Job Posting | MO | As an MO, I want to create a job posting so that I can recruit TAs for a module or activity. | MO can create a posting with title, description, skills, deadline, quota and workload; required fields are validated; new jobs appear in the TA job list. | Must | 5 | Iteration 1 | Core | Suggested explicitly in handout.
PB-11 | Job Maintenance | MO | As an MO, I want to edit or close a job so that the vacancy stays accurate. | MO can update job details before the deadline; MO can close a job; closed jobs can no longer accept new applications. | Must | 3 | Iteration 2 | Core | Needed for realistic workflow.
PB-12 | Applicant Review | MO | As an MO, I want to review applicants for a job so that I can compare candidates. | MO can see applicant list, profile summary, CV text, skills, availability and current workload; list is limited to applicants for the selected job. | Must | 5 | Iteration 2 | Core | Supports selection decisions.
PB-13 | Applicant Decision | MO | As an MO, I want to shortlist, accept or reject applicants so that the recruitment process can move forward. | MO can change status to shortlisted, accepted or rejected; quota rules are enforced; TA is able to see the updated status. | Must | 5 | Iteration 2 | Core | Core recruiting outcome.
PB-14 | Workload Dashboard | Admin | As an admin, I want to see each TA's total workload so that work can be distributed fairly. | Admin dashboard shows accepted assignments and total workload for every TA; data refreshes after status changes; overloaded users are clearly flagged. | Must | 5 | Iteration 2 | Core | Suggested explicitly in handout.
PB-15 | Workload Guardrail | Admin | As an admin, I want the system to warn when workload limits are exceeded so that MOs avoid over-allocation. | System shows warning before accepting a candidate whose workload exceeds a configurable threshold; warning is recorded in the audit trail. | Should | 3 | Iteration 3 | Extension | Supports fairness objective.
PB-16 | Job Recommendation | TA | As a TA, I want recommended jobs ranked for me so that I can focus on the most suitable opportunities. | System ranks jobs using skill match, availability and workload balance; each recommendation shows a score and brief explanation; recommendations update when profile changes. | Should | 8 | Iteration 3 | Extension | Primary AI-powered feature.
PB-17 | Candidate Ranking | MO | As an MO, I want applicants ranked for a job so that I can shortlist faster. | System ranks applicants by required skill match, preferred skill match, availability and workload balance; ranked list includes explanation for each candidate. | Should | 8 | Iteration 3 | Extension | High-value recommendation feature.
PB-18 | Missing Skill Insight | TA | As a TA, I want to see missing skills for a job so that I know how to improve my fit. | For each viewed job, system highlights matched skills and missing skills; explanations are understandable and based on structured rules or extracted keywords. | Should | 5 | Iteration 3 | Extension | Explainable AI requirement.
PB-19 | Validation & Error Handling | All users | As a user, I want clear validation and error feedback so that I can recover from mistakes quickly. | Invalid input produces readable messages; missing files or unavailable records do not crash the system; error cases are demonstrated in test cases. | Must | 3 | Iteration 2 | Core | Important for demo and acceptance tasks.
PB-20 | Audit Trail | Admin | As an admin, I want an audit trail of important actions so that decisions can be reviewed later. | System records login, job posting, application, status update and workload warning events in text-based logs; logs can be viewed or exported as CSV. | Should | 5 | Iteration 4 | Extension | Useful for governance and viva discussion.
PB-21 | Concurrent Submission Safety | System | As the system, I want to prevent duplicate or lost applications under concurrent access so that records remain correct. | Parallel submissions do not create duplicate records for the same TA and job; successful applications are persisted safely; concurrent tests prove consistency. | Should | 8 | Iteration 4 | Extension | High-concurrency showcase.
PB-22 | Atomic File Persistence | System | As the system, I want atomic file writes and safe reloads so that text files are not corrupted. | Writes use temp-file plus rename or equivalent safe mechanism; recovery from partial failure is tested; data can be reloaded after restart. | Should | 5 | Iteration 4 | Extension | Essential without database.
PB-23 | Performance Optimisation | System | As the system, I want fast read performance for popular pages so that multiple users can browse smoothly. | Job browsing and recommendation pages use cached in-memory indexes or equivalent optimisation; repeated reads remain responsive under load test. | Could | 5 | Iteration 4 | Extension | Supports scalability story.
PB-24 | Acceptance Test Support | Teaching team | As the teaching team, I want the system to support end-to-end acceptance testing so that required tasks can be demonstrated reliably. | Core scenarios for TA, MO and Admin can be executed in sequence; sample data is provided; README and user manual explain setup and testing steps. | Must | 5 | Iteration 4 | Core | Directly supports final viva and marking.