## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
1 | Module requirements posting | As a Module Organiser, I want to post the key TA recruitment information for my module, So that students can view the available TA positions and apply for them. | Must have | version1.1 | * MO can enter module code/name, number of TAs required, required skills, working hours, and application deadline. * The system prevents posting until all required fields are completed. * After saving, the job post appears in the TA job list. | 3
2 | TA profile creation | As a TA applicant, I want to create my applicant profile, So that I can submit my personal and academic information once and reuse it for applications. | Must have | version1.1 | * TA can create a profile with required fields: name, student ID, email, programme, and availability. * The system displays an error if any required field is empty. * After saving, the profile details are stored and can be viewed again by the TA. | 3
3 | CV upload | As a TA applicant, I want to upload my CV to the system, So that Module Organisers can review my qualifications during recruitment. | Must have | version1.2 | * TA can upload one CV file in PDF or DOC/DOCX format. * The uploaded CV is linked to the TA profile and can be opened by authorised Module Organisers. * The system shows an error message if the file type is invalid or no file is selected. | 3
4 | Module information display | As a TA applicant, I want the system to display clear information about TA jobs, So that I can understand the requirements before applying. | Must have | version1.2 | * The job list shows module code/name, required skills, working hours, and number of TA positions. * TA can open a module detail view from the job list. * Only currently open job posts are shown to TA applicants. | 2
5 | Module selection | As a TA applicant, I want to select up to three modules to apply for, So that I can apply for multiple opportunities while keeping my workload manageable. | Must have | version1.3 | * TA can add open modules to an application list. * The system prevents selection of more than 3 modules. * Selected modules remain visible until the application is submitted or removed. | 3
6 | Selected module count display | As a TA applicant, I want to see how many modules I have already selected, So that I can know whether I have reached the application limit. | Must have | version1.3 | * The system shows the current number of selected modules on the application page. * The counter updates immediately after each select or remove action. * A warning message is displayed when the TA reaches 3 selected modules. | 2
7 | Application confirmation receiving | As a TA applicant, I want to receive confirmation after submitting my application, So that I know my application has been successfully recorded. | Must have | version1.3 | * TA can submit the selected modules as an application. * After submission, the system displays a confirmation message with the submitted module list. * The application is stored with status "Submitted". | 2
8 | Applicants viewing | As a Module Organiser, I want to view a list of students who have applied for my module, So that I can evaluate the applicants efficiently. | Must have | version1.4 | * MO can open a list of applicants for each module they manage. * Each row shows applicant name, student ID, and current application status. * The list only contains applicants for the selected module. | 3
9 | CV viewing | As a Module Organiser, I want to view each applicant's CV with one click, So that I can assess their experience and suitability without searching through separate files. | Must have | version1.4 | * MO can open an applicant CV directly from the applicant list. * The opened CV matches the selected applicant. * If no CV has been uploaded, the system displays "No CV uploaded". | 3
10 | Application acceptance and rejection | As a Module Organiser, I want to accept or reject applicants directly in the system, So that I can complete the recruitment process more efficiently. | Must have | version1.5 | * MO can mark an application as Accepted or Rejected. * The updated decision is saved immediately after confirmation. * Only one final status is stored for each application. | 3
11 | Application status checking | As a TA applicant, I want to check the status of each of my applications, So that I can know whether each application is submitted, under review, accepted, or rejected. | Must have | version1.5 | * TA can open a status page showing each applied module and its current status. * The status page supports at least Submitted, Under Review, Accepted, and Rejected. * Changes made by Module Organisers are visible to the TA after refresh or re-login. | 2
12 | Page response speed | As a TA applicant, I want the system to load pages quickly, So that I do not waste time waiting when applying or reviewing applications. | Should have | version2.1 | * Main pages load within 2 seconds in normal local testing. * Submitting an application or opening the applicant list completes within 3 seconds. * The system shows a clear loading or error message if an operation fails. | 2
13 | Private information protection | As a TA applicant, I want my personal information to be protected, So that only authorised users can view my details. | Should have | version2.1 | * TA can view only their own profile and applications. * Module Organisers can view applicant details only for modules they manage. * Unauthorised access shows an "Access denied" message. | 3
14 | Simple interface | As a Module Organiser, I want the interface to be simple and easy to use, So that I can understand how to use it without training. | Should have | version2.2 | * Core MO actions (view applicants, view CVs, accept/reject) are reachable within 3 clicks from the dashboard. * Buttons and labels use clear action words such as View CV, Accept, and Reject. * No required controls are hidden or overlapped at normal screen size. | 2
15 | Current recruitment overview | As an Administrator, I want to view all current TA jobs and active applications, So that I can oversee the live recruitment process. | Should have | version2.3 | * Admin can view all currently open job posts in one screen. * Admin can view the current number of applications for each open job. * Admin can filter the overview by module or status. | 3
16 | Recruitment record display | As an Administrator, I want to view historical TA recruitment records in one place, So that I can review completed recruitment cycles. | Should have | version2.3 | * Completed recruitment records remain stored after the cycle closes. * Admin can search records by module or semester. * Each record shows the final applicant decision history. | 3
17 | Real-time applicant count display | As a TA applicant, I want to see the real-time number of applicants for each module, So that I can make a better application decision. | Should have | version2.3 | * The job list displays the current applicant count for each module. * The count increases after a successful new application submission. * Updated counts are visible after refresh or re-opening the page. | 3
18 | Suitable candidate identification | As a Module Organiser, I want the system to help identify suitable applicants, So that I can review strong candidates more efficiently. | Could have | version3.1 | * The system ranks or flags applicants using at least skills, experience, and availability. * The ranking result shows which criteria were matched. * Module Organisers can still manually review and override the final decision. | 5
19 | TA workload monitoring | As an Administrator, I want to monitor each TA's workload, So that I can avoid over-allocating accepted applicants. | Could have | version3.2 | * Admin can view the number of accepted TA assignments for each student. * The workload total is calculated from accepted applications only. * The system highlights students whose accepted module count exceeds the configured limit. | 5